## Sheet1
| WDD_Project_2025 | Done Y/N? | Team Member
Week | Goals for this week
Week 8 |  | Done Y/N? | Team Member
Read brief & be familiar with it |  | Yes | All group
Brainstorm with group - what sustainability goal to use |  | Yes | All group
Team member strengths and weaknesses |  | Yes | All group
1 person creates a shared folder and shares it! |  | Yes | Thales
My own wireframe |  | Yes | All group
Sitemap for whole website |  | Yes | Rúbia
Each student should create their one github repository |  | Yes | All group
Create word document and organize first submission |  | Yes | Thales
Add tasks and sign them |  | Yes | All group
Week 9 |  | Done Y/N? | Team Member
Create/Design Logo for the website |  |  | Thales, Savio
Add boostrap to your page |  |  | All group
Create Folder Structure |  |  | Maheus
Record who contributed - meeting and coding |  |  | All group
Page skeletons using Bootstrap grid; responsive checks (mobile ~375px and desktop ≥1200px). |  |  | All group
Add meta tag and name the author in every page and block of code |  |  | All group
Identical navbar and footer on every page |  |  | Thales,Matheus
Add meta tag and name the author in every page and block of code |  |  | All group
Look for interactive functions that we can add in the navbar |  |  | Rubia
Week 10 |  | Done Y/N? | Team Member
Define Color Palette and Typography |  |  | Rúbia
Custom Component Styling |  |  | Thales, Savio
Spacing and Layout Adjustments |  |  | Matheus
Test on major breakpoints |  |  | Savio
Adjust Images |  |  | Rúbia
Navigation Check |  |  | Thales
Check Page Load Speed |  |  | Matheus
Simple Transitions/Animations |  |  | All group
Test on Different Browsers |  |  | All group
Week 11 |  | Done Y/N? | Team Member
Keyboard Navigation |  |  | Rubia
Image Optimization |  |  | Matheus
Code Review and Cleanup |  |  | Thales
Device Simulation |  |  | Sávio
Forms and Validation |  |  | Rúbia
Custom 404 Page |  |  | Matheus
Week 12 |  | Done Y/N? | Team Member
Add meta tag and name the author in every page and block of code |  |  | All group
Final responsive review and accessibility check. |  |  | Savio
Create README (explain the website, process of creation, reason, issues faced |  |  | Rubia, Matheus
Write final report |  |  | Rubia, Matheus
Verify comments and meta tags across all pages |  |  | Savio
Final tidy-up, zip the site, tag a release on GitHub, and submit before the deadline |  |  | Thales
Submission | SUNDAY | Done Y/N? | Team Member
| Send FInal Submission |  | Thales